## DDS Tracker
SNo | Functional/Technical component Description | Complexity | Start Date | End Date | Owner | Status | Completion % | Comments
Pre requisite:
1 | Test Data collection & DB migration
1.1 | VIN Generator
1.1.1 | Analysis VIN details from various source - DB, UI or Open sources | Medium | 2024-08-07 | 2024-08-07 | Mukund | In Progress | 40%
1.1.2 | Automate the data fetching from various source into excel | Medium | 2024-08-08 | 2024-08-09 | Mukund | Not Started
1.1.3 | Store all the VIN details into DB | Medium | 2024-08-09 | 2024-08-09 | Mukund | In Progress | 50% | Working on inserting data into MS SQL Server in local system.
1.2 | Zipcode with Address details - County, City & Geo Code(Zip +4)
1.2.1 | Analysis Zipcode details from various source - DB, UI or Open sources | Medium | 2024-08-07 | 2024-08-07 | Barath | In Progress | 20% | Retrieved zipcodes from online; need to check on retrieval of address
1.2.2 | Automate the data fetching from various source into excel | Medium | 2024-08-08 | 2024-08-09 | Barath | Not Started
1.2.3 | Store all the Zipcode details into DB | Medium | 2024-08-09 | 2024-08-09 | Barath
1.3 | Scorecard Details & Customer profiles
1.3.1 | Identify the Scorecard for all the products and group it | Medium | 2024-08-09 | 2024-08-09 | Dolly | In Progress | 67%
1.3.2 | Preparation of Scorecard dump | Medium | 2024-08-12 | 2024-08-13 | Dolly
1.3.3 | Store all the inputs into DB | Medium | 2024-08-13 | 2024-08-13 | Dolly
1.4 | Rules Engine
1.4.1 | Grouping of Tolerance rules | Medium | 2024-08-07 | 2024-08-07 | Vijay/Team | In Progress | 45%
1.4.2 | Grouping of Decision rules | Medium | 2024-08-08 | 2024-08-09 | Vijay/Team | In Progress | 95%
1.4.3 | Store all the inputs into DB | Medium | 2024-08-09 | 2024-08-09 | Vijay/Team
1.5 | Checklist items
1.5.1 | Identify the checklist items and tag with different Products | Medium | 2024-08-07 | 2024-08-08 | Vijay/Team
1.5.2 | Store all the inputs into DB | Medium | 2024-08-08 | 2024-08-08 | Vijay/Team
1.6 | Loan formula Calculation (LTV/FCL/PTI/DTI/Residual)
1.6.1 | Criteria identification for financial validation | Medium | 2024-08-07 | 2024-08-07 | Dolly
1.6.2 | Criteria identification from PRISM for Residual calculation | Medium | 2024-08-08 | 2024-08-08 | Dolly
1.6.3 | Preparation of Test Data dump with different criterias | Medium | 2024-08-09 | 2024-08-12 | Dolly
1.6.4 | Store all the inputs into DB | Medium | 2024-08-12 | 2024-08-12 | Dolly
2 | Standalone Utilies
2.1 | Letter & PDF Validation
2.1.1 | Grouping of Letter rules, Prepare test data & Store in DB | Medium | 2024-08-12 | 2024-08-12 | Vijay/Team
2.1.2 | Automate the file with UI comparison | Medium | 2024-08-12 | 2024-08-13 | Vijay/Team
2.2 | Existing Application identification
2.2.1 | Automate the app id details from Contract info into excel | Medium | 2024-08-08 | 2024-08-08 | Nisha | In Progress | 25% | Started with data retieval from My Deals page
2.2.2 | Automate the app id details from UW - Scorecard & Decision Rules into excel | Medium | 2024-08-09 | 2024-08-12 | Gowthami/team
2.2.3 | Store it into DB | Medium | 2024-08-13 | 2024-08-13 | Gowthami/team
3 | ML implementation for Test data suggestion
3.1 | Analysis of Feature and Target variables | Medium | 2024-08-14 | 2024-08-14 | Dolly/Gowthami
3.2 | Retrieval of Training data for ML algorithm | Complex | 2024-08-16 | 2024-08-19 | Barath/Derick
3.3 | Choosing and training ML model | Very Complex | 2024-08-20 | 2024-09-27 | Barath/Derick
3.4 | Evaluation of predictions and store result in DB | Very Complex | 2024-09-28 | 2024-09-02 | Barath/Derick
3.5 | Re-feeding data to model from DB | Complex | 2024-09-03 | 2024-09-05 | Barath/Derick
4 | Centralized Platform
4.1 | Planning and development of UI structure | Complex | 2024-09-06 | 2024-09-09 | Gowthami/team
4.2 | Backend integration with DB | Very Complex | 2024-09-10 | 2024-09-12 | Gowthami/team
4.3 | Testing and evaluation | Complex | 2024-09-13 | 2024-09-13 | Gowthami/team
5 | Chat Assistant BOT
5.1 | BOT development | Very Complex | 2024-09-16 | 2024-09-18 | Gowthami/team
5.2 | Integration with centralized platform | Very Complex | 2024-09-19 | 2024-09-23 | Gowthami/team
5.3 | Testing and validation | Complex | 2024-09-24 | 2024-09-25 | Gowthami/team
5.4 | Deployment and Monitoring | Complex | 2024-09-26 | 2024-09-30 | Gowthami/team

## Individual Task
Date | Associate Name | Task Peformed | Status | Completion %
2024-12-08 | Nisha | Working on Bluebolt initiative task | In-Progress | 40%
1. Code development for retriving contact info - Disclosure information details
| Barath | 1. Overall high level KT given to Girish.
2. Worked on KM Portal.
| Girish | 1. KT recived from barath
2. Analysis of requiremets
3. initial ui design concepts
| Krishna | 1. Working on inserting data into MS SQL Server in local system. | In-Progress | 50%